## Waterfall Project Management
|  |  | Project start date | 2020-12-03
|  |  | Project Due Date | 2021-02-28
|  |  | Display week | 1
[6 empty] | 2020-12-03 | [6 empty] | 2020-12-10 | [6 empty] | 2020-12-17 | [6 empty] | 2020-12-24 | [6 empty] | 2020-12-31 | [6 empty] | 2021-01-07 | [6 empty] | 2021-01-14 | [6 empty] | 2021-01-21 | [7 empty] | 2021-01-29 |  |  | 2021-02-01 |  |  | 2021-02-04
 | time axis 2020-12-03 to 2021-02-04
Task | Assigned To | Progress | Start | Duration | End | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
Requirement Analysis
Define Project scope | Snigdha, Ornob | 100% | 2020-12-03 | 4 | 2020-12-07
Research Review | Snigdha, Ornob | 100% | 2020-12-07 | 4 | 2020-12-11
User Research | Snigdha, Ornob | 100% | 2020-12-11 | 4 | 2020-12-15
Requirement Gathering | Snigdha, Ornob | 100% | 2020-12-15 | 4 | 2020-12-19
Meeting | All | 100%
System Design
Initialize Design Definition | Snigdha | 100% | 2020-12-19 | 4 | 2020-12-23
Obtain System Element | Snigdha | 100% | 2020-12-23 | 4 | 2020-12-27
Manage Design | Snigdha | 100% | 2020-12-27 | 4 | 2020-12-31
Design Flowcharts | Snigdha | 100% | 2020-12-31 | 5 | 2021-01-05
Design UML | Snigdha | 100% | 2021-01-05 | 5 | 2021-01-10
Implementation
Coding of Back-End | Ornob, Gourab | 100% | 2021-01-10 | 5 | 2021-01-15
Review | Ornob, Gourab | 100% | 2021-01-10 | 1 | 2021-01-11
Interface Design | Ornob, Gourab | 100% | 2021-01-11 | 5 | 2021-01-16
Review | Ornob, Gourab | 100% | 2021-01-16 | 1 | 2021-01-17
Final | Ornob, Gourab | 100% | 2021-01-17 | 2 | 2021-01-19
Testing
Defining Test Cases | Ornob | 100% | 2021-01-19 | 2 | 2021-01-21
Unit Testing | Ornob | 100% | 2021-01-21 | 1 | 2021-01-22
Passed | Ornob | 100% | 2021-01-22 | 1 | 2021-01-23
Deployment
Deployment Preparation and Procedures | Ornob, Snigdha | 100% | 2021-01-23 | 1 | 2021-01-24
Product Deployment | Ornob, Snigdha | 100% | 2021-01-24 | 1 | 2021-01-25
Closing Deployment Phase | Orno, Snigdha | 100% | 2021-01-25 | 1 | 2021-01-26
Maintenance & Documentation
Modification | Himadree, Zakaria | 100% | 2021-01-26 | 1 | 2021-01-27
Error Handling | Himadree, Zakaria | 100% | 2021-01-27 | 1 | 2021-01-28
Client Support | Himadree, Zakaria | 100% | 2021-01-28 | 1 | 2021-01-29
Documentation | Himadree, Zakaria | 100% | 2021-01-29 | 5 | 2021-02-03
Hostel Managment System